## Approach
ctcLINK DEPLOYMENT GROUP 2 (DG2) GO-LIVE LESSONS LEARNED Oct. 14, 2019: Tacoma Community College, Community Colleges of Spokane (CCS) upgrade Oct. 28, 2019: Clark College, SBCTC Agency conversion/initial implementation Approach • Lessons learned will be reviewed and considered for future deployment groups. In addition, some items have already been incorporated and implemented for DG3 and DG4. • The summary will be shared with the PMs in the system, ctcLink Governance Groups and Quality Assurance (OCIO & Moran). A final document will be stored in the cDR (ctcLink Document Repository). ctcLink PMO team conducted lessons learned with the following Deployment Group 2 Stakeholder Groups: Nov.12, 2019 ctcLink Functional Team Members & Legacy Financial Aid Representation Nov. 13, 2019 ctcLink Technical Team Members & Customer Services Director Legacy) Nov. 13, 2019 DG2 Agency & Colleges: Clark (SMEs & PM), SBCTC (SME, Interim PM and Executive Sponsor), Spokane District PM, Tacoma PM Nov. 14, 2019 SBCTC Agency Directors/Leads Dec. 16, 2019 Clark Project Team requested a follow-up lessons learned session with Christy Campbell, Tara Keen & Janelle Runyon Key topic areas • Global Design Adoption (GDA), Business Process Fit Gap (BPFG), Data Conversion & Validation, UAT/Parallel Testing, Security, Organizational Change Management/Communications, Training, Go-Live/Support and ERP Support
Compiled by ctcLink Project Management Office ¦ Quality Assurance, Risk & Issue Management
ctcLink Methodology

## GDA
Global Design Adoption Lessons Learned | Description/Issue | Recommendation | Source | Status
Check Pre-Reqs | work with PMs to check completion of GDA prior to BPFG | add a check box to registration sheet for college PMs to validate completion of GDAs | FIN | In Process
Content Updated | CS team didn't have time to update this prior to distributing to DG4 | recommend updating content for accuracy | CS Core | In Process
Course Assessment | no current assessment | develop assessment to identify gaps | FIN | Complete
Design | takeaways not clear of global and local configuration (ex: grants data and PI) | document that shows what it is local and global and where items are located and how it ties to ticket | Clark | In Process
Feedback Loop on Global Decisions | example: annual schedule or other items that goes to commissions and councils and the final decision for these items | need approach to communicate and track decisions on global level | Clark | In Process
High level time frame for activities | future DGs would like to know when they will start this activity and would like their schedule | time frame for GDA activities are defined in project schedule | PMO | Complete
Survey Results | results and have we met the target and incorporate the gaps in to BPFG content | send prior to DG4 finishes GDA | FIN | Complete

## BPFG
Business Process Fit/Gap Lessons Learned | Description/Issue | Recommendation | Source | Status
BPFG & Documentation | helpful to complete documentation and change impact analysis items with SMEs and also ctcLink team during the BPFG sessions and helpful for data validation activities also | suggest to other DGs to get this work done at the session | Clark | Complete
Design | takeaways not clear of global and local configuration (ex: grants data and PI) | document that shows what it is local and global and where items are located and how it ties to ticket | Clark | In Process
Parking Lot - Follow Up | teams all communicated differently and most often they were not followed up on | centralized place for parking lot items similar to risk and issue log or cDR for ease of access | Clark | In Process
Front Line Staff | Front Line Staff Exposure to BPFG and Configuration | Recommend attending via WebEx and also communicate from key lead SMEs to front line staff (this recommendation has been shared to the PMs) | CS Core | Complete
Project Responsibility and College Responsibility | Emphasize responsibility of project staff and responsibility of college staff for implementing business and configuration decisions | Identify and communicate roles and responsibliities for facilitators and SMEs for BPFG sessions. | CS Core | Complete
Time for Assignments & Change Management in Session | Continue to ensure dedicated time for going over assignments and discussing change management during each session | Time allotted in DG4 BPFG agendas | CS Core | Complete
Timing Allotted in Project Plan | 1. Provide enough time between BPFG sessions where SMEs overlap and also when assignments are due 2. Provide enough time between BPFG sessions and conversion cycles | Already solutioned for DG4 schedule | CS Core | Complete
Walk Through Homework Template | incorporate this in to the BPFG session | continue to walk through some of the homework | FA | Complete
Clarification on Glossary of Roles / Who Should Participate? | roles could be more clear so colleges understand who to send | update and communicate the roles doc and walk through during the kick off for BPFG (and other project activities) for each pillar and follow up during the DG bi-weekly calls | FIN | Complete
Configuration Workshops Mandatory | in person participation is critical for these types of workshops | encourage same participation to keep information consistent, can not only be one person needs to be a minimum of 2 people | FIN | Complete
Course Assessment | no measurement tool to identify gaps | need a paper-based assessment (standard template) | FIN | In Process
Registration Sheets Print as Sign In Sheets | streamline process; FIN team is tracking this information in one note as a follow up to who attended | print for each session and fill in gaps | FIN | In Process
Need to focus on changes to business process and changes in org. structure (i.e. a former Payroll function may now be an HR function) | End Users are still trying to figure out who is responsible for specific functions and processes now that they're live. | Emphasize this in more detail during BPFG sessions | HCM | In Process
High-level time frame for activities | future DGs would like to know when they will start this activity and would like their schedule | time frame for BPFG activities are defined in project schedule | PMO | Complete
Aligning SF / FIN session schedule and homework | example: item types | meet to discuss alignment opportunities for DG4 and revise schedule | SF | Complete

## Data Conversion & Validation
Data Conversion & Validation Lessons Learned | Description/Issue | Recommendation | Source | Status
Documentation | documentation on how are we converting data out of legacy and where is it going to go (period of time and specific to FIN) | provide mapping documentation | Clark & SBCTC PM | Complete
Conversion Dashboards | Improve(d) dashboard data. Have worked with tech team to improve many | Evaluate additional improvements | CS Core | Complete
Conversion Weekend Fixes | Challenging but doable with Clark, not feasible for DGs with many colleges | Conversion cycles #1-#4 need to be successful and final validation cycle #5 to eliminate fall out during go-live weekend. | CS Core | In Process
Oracle Test Manager (OTM) Training for Colleges | Dedicated time to walk through how to submit items in OTM, separate from the scheduled validation workshops | OTM Training is now part of data validation workshops and UAT. | CS Core | Complete
Timing for CS | Critical overlaps in conversion and validation activities (example - Cycle 2 and Cycle 3 activities overlapped) Need to ensure enough time between: 1. Functional Validation and College Validation - did not have enough time to validate, prep materials for college, and publish to necessary locations 2. College Validation and Next Cycle Snapshot - often overlapped, eliminating any ability to critically review and make necessary changes, especially critical between cycle 2 and cycle 3 | The project schedule is reviewed weekly and project and college resource constraints are evaluated as well. | CS Core | Complete
Update GCR (Gold Change Request) Log | Adding fields to provide clear communication from functional to tech team and mark complete in work flow, example - DG, Institution, Environments Requested | Team is evaluating more efficient ways to track. | CS Core | Ongoing / Continual Improvement
Define Conversion Scope | ex: checklist uncovered in dual processing | FA team resolved this by updating checklist. | FA | Complete
Pre-SAP Environment Prep | if in middle of the term, configuration impacted (dependent on enrollment config) | FA team developed a fix; approach to split up this manual work | FA | Complete
Crosswalk Data Quality | for FIN team, account values and department values missing/duplicate at cutover | improve quality of the crosswalk data through tech checks and balances processes; crosswalk data would also be helpful for FA Dual Processing | FIN | In Process
Project Activity ID load | Excel to CI load takes a lot of time to load | plan is to pre-load some of the config data prior to cutover | FIN | In Process
Quality of Validation | how can we drive better validation for the colleges? how we can engage differently? (ties to line 3-5) | PM pass or sign off each validation cycle using OTM or paper-based; walk through this expectation during DG Bi-Weekly meeting | FIN | In Process
Absence balances for faculty were not stored in Legacy system. | Clark did not store some faculty absence balances in Legacy.There was a request made prior to go-live to include this detail as part of the conversion.An ad-hoc rule was put in place to accommodate the request. | Recommend that subsequent colleges store all required absence balances in the legacy system. Solution needs to be a priority for DG3. | HCM | Complete
Absence Data Cleanup in Legacy | Clark did not cleanup the personal holiday and personal leave balances within the legacy system.The leave balances should have had been converted from days to hours.A special program was created convert these balances. | Recommend that subsequent colleges adjust absence data and store it in their system. Solution needs to be a priority for DG3. | HCM | Complete
Concerns regarding the conversion to validation timing and the monitoring of the accuracy of the validation. | The timing of the data conversion cycles in conjunction with the allowed time to validate errrors/issue was not sufficient.Issues and kickouts seen in early conversion cycles were not addressed and still present in later cycle. | Continue to evaluate conversion and data validation timelines. | HCM | Ongoing / Continual Improvement
Conversion Snapshot Data Issue - Absence/Time & Labor (TL) | Employees were not able to submit absence requests from the beginning of the aligned pay period (10-16).The colleges were instructed to capture the absence requests and send to the project team.The project team is loading a one time update to address the issue. For subsequent DG rollouts, an absence row will be added to job data and paygroup change to map the employees in the absence systems to the begining of the period.The TL enrollment and comp time enrollment date associated also needed to align.The conversion logic was updated to handle the associated TL date logic change. | Recommendation is to leverage the updated TL conversion logic and for absence to leverage the inserted job data row and paygorup change for all subsequent rollouts. Solution needs to be a priority for DG3. | HCM | Complete
Validation of Email Address | Some employees had a personal, missing, or test email converted/associated with their contact details. The associated User Profiles built of the personal data were inaccurate based on the above. | Work Email need to be in place and validated in the email field on screen PS0004 | HCM | Complete
Validation of Job Data fields | Lack of validation resulted in lots of manual fixes in PeopleSoft for the End Users.(i.e. empl_class, deptid, ern_code, combo_code) | Validate all fields as directed in the Data Validation Guide provided by the Project Team.Discuss approach to validation across pillars/modules. | HCM | Complete
Validation of Supervisor | Some employees were converted with no Supervisor ID assigned in Job Data. This prevents Time/Absence requests from being routed to a supervisor for approval. | Supervisor assigned on screen PS0002 must be active. The field cannot be blank | HCM | Complete
Data Clean Up Instructions (Quarterly) | provide more clarity on process and distinguish quarterly versus data clean up actvitiies during implementation | add links to communications email and cDR | PMO | In Process
Security / Empl ID/ Cycle 3 | demo environment with standard set of configuration | need an environment with these components (suggested during BPFG) | PMO | In Process
GCR (Gold Change Request) Process | changes were not communicated (DMS tables) and there's a reporting impact | Provide well in advance of conversion weekend project team needs to provide value changes and also support needs to be able to communicate back to project team. Need a centralized person at SBCTC Support Manager to help coordinate these efforts. | SBCTC Support | In Process
Dedicated Environment | fixes need to be migrated to dedicated environment; would be helpful for payroll activities as well | Dedicated environments have been provided. | SF | Complete
Reports & Querries | would confirm that data configuration comes across the environments (example: closing work) | discuss with SMEs and provide comparison reports | SF | In Process
Suppress for General Ledger | learning opportunities for what happened with DG2 to incorporate for DG3 | work with tech team on conversion approach | SF | Complete
True Validation of Accounts | for accounts that should have been zeroed out or charge priorities | Validate accounts and confirm the appropriate are zeroed out or charge priorities. | SF | Complete
Conversion Infrastructure | need to review conversion infrastructure | need to try new conversion infrastructure DG3 cycle 4 and involve managed services | TECH | Complete
Delivered Bug by Oracle | spent a lot of time going through errors at go-live and Oracle says it's resolved | reach out to Oracle prior to go-live to create SRs as needed | TECH | In Process
GCR (Gold Change Request) Cutoff | last minute requests for GCR submission and changes | need to have a cutoff date | TECH | In Process

## UAT Parallel Testing
UAT / Parallel Testing Lessons Learned | Description/Issue | Recommendation | Source | Status
UAT Closure Date | need to define closure date | target date set for expectations of a stopping point for configuration changes and include in quality gate | ALL PILLARS | Complete
Testing Roles & Responsibility | Need clearly defined roles/responsibilities for each piece of the testing puzzle: shakedown, staging, security, responding to submitted issues, escalating issues, etc. | Continue to define and improve roles and responsiblities. | All Pillars | Ongoing/Continual Improvement
OTM Training for Colleges | Dedicated time to walk through how to submit items in OTM | OTM training is provided as part of UAT kick off as well as supporting documents. | All Pillars | Complete
Source of UAT Items | unsure of decisions and the root of where those came from GDA/CPW; not communicated but appeared in testing | increased communication or user friendly description or source of the GDR, BPFG or CPW | CCS | Complete
CS 9.2 | worked well for CS 9.2 along with training documentation | N/A | CCS | Complete
Timing | not a lot of notice or time | allow for more time | CCS | Complete
HCM Image Updates | communicate what this includes (ex: payroll in the subject line) | This is tied to post support and we have provided this information to appropriate leaders handling maintenance. | CCS | Complete
End to End Testing | SF was lacking, along with integration testing between pillars and end to end testing (HCM & GL), scripts were not provided | Three parallel testing cycles allow for end to end testing. | CCS/SBCTC/ERP | Complete
Regression Testing | not a clear picture of who and what is needed to be tested | Clearly define what is regression testing which allows colleges to retest any areas that were not successful or needed additional testing. | Clark and CCS | Complete
Account Set Up /Data Staging | role and access not set up in advance along with appropriate QRGs | PeopleSoft Security Re-Design of roles and permission list have been completed. Supporting document is updated to help colleges assign the right access to employees and to evaluate this prior to UAT. | Clark | In Process
FWL Testing | SME resources didn't understand the scope and time frame so this interfered with FWL testing | Communicate appropriate SMEs for FWL to be involved in other project activities so they are prepared for testing. | Clark | Complete
Configuration & Data Sources | Challenge with environment build, especially with which conversion cycle is used to populate and which environment is used to source the configurations (functional, security, projects, etc.) | Tight timelines have impacted environment builds with appropriate conversion cycle. | CS Core | In Process
Environment | environment was not available for end to end testing with the apppropriate set up | ERP Support Staff needs to align and be available to participate in UAT and Parallel Testing. | ERP | Complete
SME Testing Order | FA SMEs testing out of order so issues arose in OTM | Communicate clear expectation with SMEs on testing and in sequence. | FA | Complete
Dual Processing | need more testing scenarios | need to test different scenarios (ex: job set, multiple terms) | FA | Complete
Approval Workflow | Requests to rule changes were reported after the UAT completion timeframe and security was not ready so they had to use SVL. | The methodology includes a Sandbox for the colleges but since Security was delayed an environment has not been provided. A Sandbox will be provided for DG4. | FIN | In Process
Payroll parallel testing approach / scope | One parallel was planned and at least three occurred.The data for first parallel was the only round with accurate data.The later rounds were comprised mocked up data. | Expect one parallel test round and ensure colleges are prepared for the testing effort involved. | HCM | In Process
Absence related changes from UAT - Rule Changes | Requests to rule changes were reported after the UAT completion timeframe. | Request that all configuration related feedback / requests are received during the UAT testing before moving to production. | HCM | Complete
Parallel Testing Connectivity | challenge to set up network connectivity to that environment; had to open firewall for colleges to access | need to change the way we grant access to the environment or build a better process for user IP addresses in advance | LEGACY | In Process
Provisioning of User Accounts - Legacy | difficult to get a consolidate list of users for various environments | need to think of a better process for collecting this information for the volume of DG3 schools and beyond | LEGACY | In Process
Entrance and Exit Criteria | we didn't follow the criteria or hold ourselves accountable to the criteria | Continue to formalize the methodology for testing. | SBCTC Support | In Process
Testing Team | recognize the work that this team put forth to revamp the approach | N/A | SBCTC Support | Complete
UAT Testing by Colleges | understand why testing is important and encourage all colleges to test | Expectations are set in UAT kick off. | TCC | Complete
FLUID Testing | testing happened at the end which caused a compression | N/A | TCC | Complete
Bank/Mobile/HigherOne | testing was incompleted and testing files on vendor on side was completed after go-live | work with the vendor to make sure the college file is loaded successfully; has been incorporated in project plan | TECH | Complete
CEMLI testing for new colleges | CEMLI cross-walks were not completed for DG2 | CEMLIs will be tested as needed for specific colleges. | TECH | Complete
Security not Established Correctly | this was not ready for UAT | Security Re-Design is now complete and supporting document being finalized for better execution for future deployments. | TECH | In Process
SF Parallel Testing Approach | this approach needs to be revisited to accomodate all items (1098, end to end) | needs to be reviewed as part of parallel scope | TECH | In Process
UAT Scope / Out of Scope | identify scope and items were not tested | define scope and ensure that testing is done (ex: CEMLIS) | TECH | Complete
Chart of Accounts | data was no in sync with current PRD and UAT environment | refresh of UAT needs to have all the current state of CoA | TECH | Complete

## Security
Security Lessons Learned | Description/Issue | Recommendation | Source | Status
Adding/Removing bulk security roles | no tool for this work | This will be a future consideration which we have provided to the SBCTC Security Organization. | CCS | Not Started
Status | lacking clear status communication during the DG calls | more open communication and better vendor management and holding them accountable | CCS | Complete
Security Delay | about a year delay with re-design (vendor and resource issues) | colleges need communication and document well in advance | CCS & SBCTC | In Process
Changing Permissions | ex: Service permissions were changed and there's no clear description of the change | knowing the changes for the permissions lists or the lists that never got brought over from zz or ctc role | Clark | Complete
Communications | documenting and communicating info regarding role changes | We have provided this recommendation to the SBCTC Support Organization. | Clark | Complete
Documentation | SACR and preferences - set up, how and when you need it | more documentation for security access | Clark | In Process
List of Roles | there is not a guide that communicates the common tasks and what they need access to and what roles are needed for that access (ex: service indicator roles) | helpful guide for common tasks to assign roles; collect what SBCTC and Clark has identified to share this information out | Clark | In Process
ctc Roles | number of folks that have this role, need to resolve these roles or remove them | DG2 roles are managed locally. | Clark and CCS | Complete
Security for All Staff | At go-live, many staff missing security roles and permissions. | Ensure security assigned to both lead SMEs and all front line staff. Recommend security review earlier in engagement process | CS Core | Complete
Security Packages | Security re-design not deployed in all the environments. | This was DG2 specific. | CS Core | Complete
Final Security Matrix | Final matrix not solidified/provided to functional team. Continues to be security role changes even post go-live. Needed for DG3 go-live. | The Security Re-Design is complete and supporting documents is being finalized. Transition will happen for DG4. | CS Core | In Process
Pages under Permissions List | access missing for specific pages in the menu | This has been resolved as part of DG2. | FA | Complete
Role being Created | process for upload /download | This has been resolved as part of DG2. | FA | Complete
Security Run Process | tied to bundle / image - to hold institution security | called update security views | FA | Complete
Empl IDs | Need a set of empl IDs to work with for prototyping processes | Cycle 2 - coordinating with refresh cycle and the data HCM needs this no later than the dry run (cycle5) | FIN | Complete
Role assignments were inaccurate | The roles were not properly assigned to end users causing issues or lack of expected functionoalty once live. | All security roles need to be defined, tested, and assigned/validated earlier in the project plan. | HCM | In Process
Security / Testing alignment | Security was not completed nor tesed during UAT.Issues that were relayed post go-live would in most cases be addessed if they were found during UAT. | Ensure security is associated as part of UAT. | HCM | Complete
Testing Security Roles | Project Team did not have a sufficient amount of time to thoroughly test the Security Roles per the redesign. | More realistic timeline for testing security | HCM/SF | Complete
Transition & Walk Through | team needs a walk through of security items for DG3 | Tara walk team through this | PMO | In Process
Roles | when something is missing, there's not a clear way to report this info (GL reports) | This is a communication issue working with IT Security to ensure there is a process to communicate to colleges. | SBCTC PM | In Process
EMPL IDs and Employee Info | provided to SBCTC for security set up but were not converted properly causing issues for after go-live (supervisor approval) | cross-walking info and verifying prior to Go-Live and provide accurate information for security set up | SBCTC Support | Complete
Training for Security Admin | lack of training opportunity for security admin | Will need to work with IT Security appropriate mainatence and training is available for security admins. | SBCTC Support | In Process

## OCM&COMMS
OCM & Communications Lessons Learned | Description/Issue | Recommendation | Source | Status
Cliff Notes Comms | high level overview for items (security, etc) | Standardized templates for communicating key activities to the colleges. | COMMS | In Process
Data Sharing | not having documentation that is clear on what data is shared and can be viewed by all | provided this input to Data Governance | CCS | Complete
Expectations / Prepare | there will be bumps after go-live, concerns to work through and just in time training | We have developed a cutover/support plan and communicated lessons learned. In addition, we have staff prepared based upon those set expectations. | SBCTC PM | Complete
KeyTopics (Working Group Enhancement Requests/Governance Decisions) | there is not a central location for key decisions | Key decisions are tracked in PWA. We are looking how to make that more visible and transparent. | PMO/CCS | Complete
OCM Activities | needs to happen after go-live (training, proficiency) | knowledge networks and OCM communications | SBCTC | In Process

## Training
Training Lessons Learned | Description/Issue | Recommendation | Source | Status
Shorter Videos & Simulations | developing more of these modes of training | The long term training strategy includes a training tool (Story Line) which includes assessments/comprehension/evaluation/pre-reqs/reporting. | COMMS | In Process
Employee Self-Service (ESS) and Manager Self-Service (MSS) Training Approach | ESS/MSS training should be considered strongly as a mix of online/in person sessions.The support questions that are being logged indicate that the training approach should be readjusted for these functions/features. | Readjust the training approach for ESS/MSS. HCM team should discuss on best approach to deliver this content. | HCM | In Process
Self-Service Training | add more depth to the content | get more feedback from SMEs | PMO | Complete
Hands-on training | SMEs wanted an environment for hands-on training | Project team is working on providing an environment. | SBCTC PM | Complete
Supervisors & Approvers | check to make sure this group has completed training | Emphasize to managers to complete the training to understand their role is critical for Manager Self-Service. | SBCTC PM | Complete
Training Team | did an amazing job to develop courses/content | N/A | SBCTC Support | N/A
College Training Leads | need a connection point with them | meet with them regularly to check in and fill the gaps | TRAINING | In Process
Environment | need environment for transaction-based training | Project team is working on providing an environment. | TRAINING | In Process
Business-Specific Training | General self-paced content does not allow for institution-specific business scenarios and questions | Colleges are providing local lessons learned on how they are doing this business specific training at the local college level. | College | Complete
Hands-On & Activity-Based Trainings | Saw need for more hands-on and activity based trainings | The long term training strategy includes a training tool (Story Line) which includes assessments/comprehension/evaluation/pre-reqs/reporting. | College | Complete
PeopleSoft Basics Trainings | Need to ensure frontline staff are included and are participating in trainings. | Colleges are providing local lessons learned on how they track local college participation in PS Fundamentals. | College | Complete
Training for Front Line Staff | Need to ensure frontline staff are included and are participating in trainings. | Colleges are providing local lessons learned on participation of front line staff in training and other key project activities. | College | Complete

## Go-Live Support
Go-Live/Support Lessons Learned | Description/Issue | Recommendation | Source | Status
Central WebEx and Support Process | worked well and quick response by project team | N/A | ALL PMs | N/A
Account lock outs | specific for FIN folks and tied to security/access | this is resolved (script issue) | CCS | Complete
Document Post Go Live | ex: cutover plan, health check guide | will provide these documents (cutover plan, support plan, health check guide) in advance | Clark | Complete
Escalation Path & Ticketing System | working out locally as well as through the ticketing system | SBCTC has provided SLAs to the colleges. Colleges need to develop their local support plan. | Clark | In Process
Incremental Roll-Out or Rolling Phases | prepare and plan for different areas to have more time before opening services or the system to students/staff (ties to item #5); need to understand who needs to be on first and what can come as secondary items | Clark recommends a week of closure; help teams have more time to process transactions (FIN/FA) | Clark | Complete
Infrastructure for Tracking Concerns | not having a process to track all the different items, requests and questions that come in and process to follow up | Clark recommends this to other colleges. | Clark | Complete
Instruction/Faculty | central point of contact and tracking and triage process for specific instruction/faculty concerns, continuous follow up for smaller items as well as the bigger concerns | Clark recommends this to other colleges. | Clark | Complete
On ground support at go-live and ERP webex for enrollment | helpful at go-live and this week by ERP team | The project team and support team participated in on the ground support at Clark to learn for larger/future DGs where that will not be possible. | Clark | Complete
Shutdown Procedures & Tasks after Go-Live | pillars were not provided clear shut down procedures or a check list of considerations pre and post go live and communication on go live date and the impact to tasks for the specific date | We have requested this from the legacy support team and we have lessons learned from Clark to share with the other colleges. | Clark | Complete
Triage | different areas set up for specific groups but centrally located was helpful | additional week could have been helpful; Clark recommends this to other colleges. | Clark | Complete
Engaging PIOs | engage with PIOs well in advance of go-live | added this to the project plan. | COMMS | Complete
ctcLink - All Hands | not having enough PMO resources on site for the month of go-live and during the weekend conversion activities | do not plan college visits during deployment month | PMO | Complete
ctcLink Go Live Food/Fun | plan this well in advance, need counts, etc. | this was very successful and will be continued in future deployments | PMO | Complete
Troubleshooting during all day webex | HCM Team received the same question(s) from multiple people at the same institution. Additionally, there would be a Help-Desk Ticket filed addressing the same issue and would cause confusion. | Need a discussion about how to route questions from end users at Go-Live | Project Team | In Process
Great Collaboration | collaboration from college/sbctc/ctclink to resolve and troubleshoot | N/A | SBCTC Support | N/A
Processes by Pillars | schedule/cut off was provided | steps / checklist / and follow up on closing and running processes that is dependent on go-live time frame | SBCTC Support | Complete
Command Center | staffing resources and rapid response to tickets | staff by all areas of ERP | SBCTC Support | In Process
Go-Live smoother | better approach overall | N/A | SBCTC Support | N/A
Go-Live Weekend Activities | timing and specifics delivered just days before so it made it tough to coordinate SMEs | map out schedule a couple of weeks in advance | TCC | Complete